PROJECT ROADMAP

When Does the Knowledge Graph Help?

Adaptive RAG Routing for EHR-Grounded Clinical Question Answering

M.Tech Computer Science · MAHE Bengaluru Target: CHIL / AMIA / EMNLP-BioNLP Total Estimated Duration: 7–9 Months

# Executive Summary & Phase Overview

This roadmap divides the project into 7 phases. Each phase has concrete deliverables, task-level breakdowns, and time estimates. Follow phases sequentially; some sub-tasks within a phase can run in parallel.

| Phase | Name | Duration | Key Output |
| --- | --- | --- | --- |
| Phase 0 | Environment Setup & Literature Review | 2–3 weeks | Working dev environment; 30-paper lit review; gap analysis |
| Phase 1 | Data Access, Lakehouse & EHR Pipeline | 3–4 weeks | MIMIC-IV loaded; Parquet lakehouse; patient snapshot API |
| Phase 2 | Medical Knowledge Graph Construction | 3–4 weeks | Neo4j MKG (~1–3k nodes, ~5–10k edges); validated 50-edge sample |
| Phase 3 | SLM Fine-tuning & Retrieval Layer | 4–5 weeks | QLoRA-tuned Phi-3 Mini; FAISS index; all 3 retrieval modes working |
| Phase 4 | Adaptive Retrieval Router | 4–5 weeks | Featurizer; pseudo-label pipeline; trained router; baselines |
| Phase 5 | Hallucination Taxonomy & Evaluation | 4–5 weeks | 300–500 annotated QA pairs; Cohen's κ; hallucination classifier |
| Phase 6 | Experiments, Analysis & Paper Writing | 5–6 weeks | Full result tables; ablations; sparsity plots; complete paper draft |

PHASE 0: Environment Setup & Literature Review [Weeks 1–3]

## 0.1  Development Environment

Set up your complete software environment before touching any data or code. This prevents version conflicts later.

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Install CUDA + PyTorch | CUDA 12.x, PyTorch 2.x with RTX 4050 support. Verify: torch.cuda.is_available() | 2 days |
| Install HuggingFace stack | transformers, peft, bitsandbytes, trl, datasets, accelerate. Pin versions to a requirements.txt | 1 day |
| Install LangChain / LlamaIndex | For RAG orchestration. Choose one as primary (LangChain recommended for flexibility) | 1 day |
| Install Neo4j Desktop | Free version. Test py2neo or neo4j Python driver with a toy graph | 1 day |
| Install DuckDB + Parquet tools | pip install duckdb pyarrow pandas. Run a test query over a small Parquet file | 0.5 days |
| Install FAISS | faiss-cpu or faiss-gpu. Test nearest-neighbor search on random vectors | 0.5 days |
| Set up Git repo | Private GitHub repo with /data, /src, /notebooks, /experiments, /paper folders. Add .gitignore for large files | 0.5 days |
| Test QLoRA on a toy model | Run a minimal QLoRA fine-tune on a small model (e.g., GPT-2) to verify bitsandbytes + PEFT work on your GPU | 1 day |

## 0.2  MIMIC-IV Access

MIMIC-IV requires credentialing through PhysioNet. Start this immediately — approval can take 2–4 weeks.

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Complete CITI Program training | Complete 'Data or Specimens Only Research' course on citiprogram.org. Download certificate. | 2–4 hours |
| Register on PhysioNet | Create account at physionet.org. Upload CITI certificate. | 1 hour |
| Apply for MIMIC-IV access | Submit credentialed access request for MIMIC-IV (v2.2 or latest). Note: this approval can take 1–3 weeks. | 1 hour |
| Download relevant tables | Once approved, download: admissions, diagnoses_icd, labevents, chartevents, prescriptions, noteevents (or discharge). These are the core tables. | 1 day |
| Verify data integrity | Row counts, null rates, date ranges. Write a small validation notebook. | 0.5 days |

⚑ Note: Apply for MIMIC-IV access on Day 1 of the project — approval latency is the biggest scheduling risk in Phase 0.

## 0.3  Literature Review & Gap Analysis

A focused literature review that directly feeds your Related Work section and sharpens your research positioning.

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Read core KG-RAG papers | MedRAG (WWW 2025), MediGRAF (arXiv 2602.00009), MedGraphRAG. Take structured notes: method, dataset, metrics, limitations. | 3 days |
| Read adaptive RAG papers | RAGRouter, RouteRAG, TAdaRAG, Self-RAG. Note: none are medical-domain focused — this is your gap. | 2 days |
| Read hallucination papers | Med-HALT, HaluEval, RAGAs, TruthfulQA. Understand existing hallucination taxonomies. | 2 days |
| Read EHR QA papers | EHR-SeqSQL, EHRAgent, clinical NLP papers using MIMIC. Note evaluation protocols. | 2 days |
| Read SLM medical papers | Phi-3 Mini, MedAlpaca, BioMistral. Note fine-tuning recipes and hardware requirements. | 1 day |
| Write gap analysis memo | 1–2 pages: what exists, what's missing, how your router fills the gap. This becomes your Introduction. | 2 days |

## 0.4  Phase 0 Deliverables Checklist

- Working Python environment with all dependencies installed and tested

- MIMIC-IV access application submitted (ideally approved)

- requirements.txt / conda environment file committed to repo

- Literature review notes (structured spreadsheet or Notion doc)

- 1–2 page gap analysis memo

- Toy QLoRA fine-tune confirmed working on RTX 4050

PHASE 1: Data Access, Lakehouse & EHR Pipeline [Weeks 4–7]

Goal: build the data foundation — a clean, query-able lakehouse — and implement the patient snapshot API. Everything downstream depends on this.

## 1.1  MIMIC-IV Ingestion

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Load core MIMIC-IV tables | admissions, patients, diagnoses_icd, labevents, chartevents (vitals), prescriptions, d_labitems, d_icd_diagnoses | 1 day |
| Convert CSV → Parquet | Use pandas + pyarrow. Partition labevents and chartevents by hadm_id or subject_id for fast per-patient queries. | 1 day |
| Set up DuckDB over Parquet | Create a duckdb connection that reads Parquet files. Write and test JOIN queries: e.g., all labs + diagnoses for a given hadm_id. | 1 day |
| Ingest clinical notes | Load noteevents (MIMIC-III) or discharge table (MIMIC-IV v2). Store as Parquet with columns: subject_id, hadm_id, text, category, chartdate. | 1 day |
| Load QA datasets | Download MedQA (USMLE train/dev/test splits), MedQuAD. Store as Parquet with columns: question, answer, split. | 0.5 days |

## 1.2  Lakehouse Schema & Organization

Organize all Parquet files under a clean directory structure:

| Folder | Contents | Key Columns |
| --- | --- | --- |
| lakehouse/patients/ | patients.parquet | subject_id, gender, anchor_age |
| lakehouse/admissions/ | admissions.parquet | hadm_id, subject_id, admittime, dischtime, diagnosis |
| lakehouse/labs/ | labevents.parquet (partitioned) | hadm_id, itemid, valuenum, valueuom, charttime, flag |
| lakehouse/vitals/ | chartevents_vitals.parquet | hadm_id, itemid, valuenum, charttime |
| lakehouse/diagnoses/ | diagnoses_icd.parquet | hadm_id, icd_code, icd_version, seq_num |
| lakehouse/medications/ | prescriptions.parquet | hadm_id, drug, dose_val_rx, route, starttime |
| lakehouse/notes/ | notes.parquet | hadm_id, subject_id, text, category, chartdate |
| lakehouse/qa/ | medqa.parquet, medquad.parquet, ehr_qa.parquet | question, answer, split, source |

## 1.3  EHR Sparsity Metrics

Implement the sparsity score S defined in the proposal. This is used for H2 analysis in Phase 5.

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Implement n_labs per hadm_id | DuckDB query: COUNT(DISTINCT itemid) from labevents WHERE hadm_id = X | 0.5 days |
| Implement n_diag per hadm_id | DuckDB query: COUNT(DISTINCT icd_code) from diagnoses_icd WHERE hadm_id = X | 0.5 days |
| Implement d_note per hadm_id | Days since last note before a given reference date. Handle missing notes. | 0.5 days |
| Compute sparsity buckets | For each hadm_id in your QA set, compute S and assign to low/medium/high bucket. Store in lakehouse/sparsity.parquet. | 1 day |
| Tune bucket thresholds | Inspect distributions of n_labs, n_diag, d_note across MIMIC-IV. Choose thresholds so roughly ~33% of cases fall in each bucket. | 0.5 days |

## 1.4  Patient Snapshot API

Write a Python function get_patient_snapshot(hadm_id) that returns a structured dict and formatted text string. This is called by the retrieval layer.

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Implement get_patient_snapshot() | Returns: demographics, last 10 labs with flags, last 5 vitals, all active diagnoses (ICD + description), active medications. | 2 days |
| Implement format_snapshot_text() | Converts snapshot dict to the formatted string used in prompts. Example: 'Patient: 65M. Diagnoses: T2DM, CKD3. Labs: HbA1c 9.1% [HIGH]...' | 1 day |
| Unit test on 10 patients | Verify correctness of snapshot for 10 manually checked MIMIC-IV admissions. | 1 day |
| Implement sparsity computation | get_patient_snapshot() should also return the sparsity bucket for that patient. | 0.5 days |

## 1.5  Synthetic EHR-QA Dataset Construction

Create the custom EHR-QA dataset from MIMIC-IV discharge summaries. This is used for both fine-tuning and evaluation (using non-overlapping patient splits).

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Define patient ID splits | Assign MIMIC-IV subject_ids to: fine-tune set (60%), router-train set (15%), router-val set (10%), held-out eval set (15%). Save splits to a JSON file. Never cross these boundaries. | 1 day |
| Define question templates | 10–15 templates: 'What is the primary diagnosis?', 'Which lab abnormality is most concerning?', 'Is [drug] appropriate given the current labs?', 'What is the recommended next step?', etc. | 1 day |
| Generate QA pairs from fine-tune split | Apply templates to discharge summaries from fine-tune patients. Use rule-based extraction where possible. Target 500–1000 pairs. | 2 days |
| Generate QA pairs for eval split | Apply templates to eval-split patients. Target 300–500 pairs. These will be manually reviewed in Phase 5. | 2 days |
| Manual quality check | Review 50 randomly sampled QA pairs. Remove or fix obviously wrong answers. | 1 day |

⚑ Note: The split JSON file is sacred. Print it and tape it to your wall. Never use eval-split patients for training anything.

## 1.6  Phase 1 Deliverables

- Parquet lakehouse fully populated and queryable via DuckDB

- get_patient_snapshot() function tested on 10+ patients

- Sparsity buckets assigned to all relevant hadm_ids

- Patient ID splits (train/router-train/router-val/eval) saved and locked

- Synthetic EHR-QA dataset (fine-tune portion + eval portion, separate files)

- MedQA + MedQuAD loaded into lakehouse

PHASE 2: Medical Knowledge Graph Construction [Weeks 8–11]

Goal: build a validated, documented MKG in Neo4j. Start with 3–5 diseases. Breadth is less important than quality and documentation — reviewers will scrutinize this.

## 2.1  Seed Entity Selection

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Choose 3–5 anchor diseases | Start with: Type 2 Diabetes, Hypertension, CKD (stages 3–5), Heart Failure, COPD. These are the most common in MIMIC-IV. | 0.5 days |
| Enumerate symptoms | List 5–10 key symptoms per disease from a trusted reference (Harrison's, UpToDate, or MeSH). Total: ~30–50 symptom nodes. | 1 day |
| Enumerate lab tests | List key labs per disease (e.g., HbA1c/glucose for DM, creatinine/eGFR for CKD, BNP for HF). Total: ~20–40 lab nodes. | 1 day |
| Enumerate treatments | First-line + second-line drugs per disease, including contraindications. Reference standard guidelines (ADA, JNC, KDIGO, ACC/AHA). | 1 day |
| Map ICD-10 codes | For each disease, list the ICD-10 codes that map to it. This links MKG nodes to MIMIC-IV diagnoses_icd. | 1 day |

## 2.2  Edge Construction: Ontology-Based

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Choose ontology source | Option A: UMLS subset via MetaMap or QuickUMLS. Option B: Disease Ontology + DrugBank. Option C: manually curated from guidelines. Start with Option C for 3–5 diseases — it is most controllable. | 1 day |
| Extract disease→symptom edges | For each disease, extract symptom relationships from your chosen ontology or guidelines. Store as CSV: (disease, symptom, relation, source). | 2 days |
| Extract disease→lab_test edges | Map each disease to its diagnostic/monitoring lab tests. Note: include normal range for each lab. | 1 day |
| Extract disease→treatment edges | Include: first_line_treatment, second_line_treatment, contraindicated_if (with condition, e.g., 'Metformin contraindicated if eGFR < 30'). | 2 days |
| Store as edge CSV | Final schema: source_node, source_type, relation, target_node, target_type, confidence, source_reference | 0.5 days |

## 2.3  Edge Construction: EHR Co-occurrence

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Compute disease–lab co-occurrence | DuckDB query: for each disease (ICD code), count how often each lab (itemid) appears in the same admission. Compute frequency and odds ratio. | 2 days |
| Apply threshold | Add co-occurrence edge if frequency > 5% of admissions with that disease OR odds ratio > 2.0. Document threshold choice. | 1 day |
| Compute disease–drug co-occurrence | Same approach for prescriptions. Add edges for frequently co-prescribed drugs. | 1 day |
| Merge ontology + co-occurrence edges | Combine both edge sets. For duplicates, keep higher-confidence source. | 0.5 days |

## 2.4  Neo4j Import & Graph Setup

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Install and configure Neo4j | Neo4j Desktop (free). Create a dedicated database for the project. | 0.5 days |
| Import nodes | Use LOAD CSV or the neo4j Python driver to import all nodes: Disease, Symptom, LabTest, Drug, Procedure. | 1 day |
| Import edges | Import all edges with relationship types and properties (confidence, source). Verify counts. | 1 day |
| Write entity linking function | map_ehr_to_mkg(icd_codes, lab_itemids, drug_names) → list of MKG node IDs. This bridges the patient snapshot to the graph. | 1.5 days |
| Write subgraph retrieval function | get_mkg_subgraph(node_ids, hops=2) → list of triples. Then linearize_triples(triples) → list of natural language strings. | 1.5 days |
| Test on 5 patient snapshots | Run entity linking + subgraph retrieval for 5 real MIMIC-IV patients. Inspect outputs for correctness. | 1 day |

## 2.5  Manual MKG Validation (Critical for Publication)

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Sample 50 random edges | Use random.sample() across all edge types. Include at least 10 edges from co-occurrence sources. | 0.5 days |
| Validate each edge | Check each edge against UpToDate, Harrison's, or a clinical guideline. Label: Correct / Partially correct / Incorrect. | 2 days |
| Remove/fix spurious edges | Remove any edge labeled Incorrect. Fix Partially correct edges where possible. | 1 day |
| Document validation results | Record: % correct before/after, error types, sources used. This table goes directly into your paper. | 0.5 days |
| Report MKG statistics | Final node count by type, edge count by relation type, density, avg. degree. This goes in your paper as a table. | 0.5 days |

⚑ Note: Even a small, well-validated MKG is publishable. A large, unvalidated one is not. Quality over quantity.

## 2.6  Phase 2 Deliverables

- Neo4j MKG with documented node/edge counts and type distributions

- Edge CSV files (ontology-based + co-occurrence) committed to repo

- Entity linking function: ICD/lab/drug → MKG node IDs

- Subgraph retrieval + linearization functions

- 50-edge manual validation table (for inclusion in paper)

- MKG statistics table (nodes, edges, by type)

PHASE 3: SLM Fine-Tuning & Retrieval Layer [Weeks 12–16]

Goal: fine-tune Phi-3 Mini with QLoRA; build the FAISS index; implement and test all three retrieval modes (T, T+E, T+E+K).

## 3.1  Phi-3 Mini QLoRA Fine-Tuning

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Download Phi-3 Mini | microsoft/Phi-3-mini-4k-instruct from HuggingFace. Confirm it loads in 4-bit on RTX 4050. | 0.5 days |
| Prepare fine-tuning dataset | Merge MedQA train + MedQuAD + synthetic EHR-QA (fine-tune split only). Format as instruction-response pairs. Target: 3,000–8,000 pairs. | 2 days |
| Configure QLoRA | Use PEFT + bitsandbytes. r=16, alpha=32, target_modules=['q_proj','v_proj']. Use 4-bit NF4 quantization. Batch size: 2–4, gradient accumulation: 4. | 1 day |
| Run fine-tuning | Use SFTTrainer from trl. 2–3 epochs. Log train/val loss. Expect ~4–8 hours on RTX 4050. | 1–2 days |
| Save LoRA adapters | Save adapter weights separately from base model. This keeps storage manageable. | 0.5 days |
| Basic generation test | Test on 10 sample questions. Confirm the model follows instruction format and produces medical text. | 0.5 days |

⚑ Note: If Phi-3 Mini exceeds VRAM: reduce batch size to 1, increase gradient accumulation to 8, or use gradient checkpointing. Monitor VRAM with nvidia-smi.

## 3.2  Embedding & FAISS Index

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Choose embedding model | Primary: BAAI/bge-small-en-v1.5 (fast, good quality). Secondary: all-MiniLM-L6-v2 (for comparison). Both run on CPU. | 0.5 days |
| Chunk clinical notes | Split discharge summaries into 256-token chunks with 32-token overlap. Use LangChain's RecursiveCharacterTextSplitter. | 1 day |
| Embed all chunks | Embed: note chunks + MedQA passages + MKG linearized triple descriptions. Store embeddings as numpy arrays with metadata (hadm_id, source, chunk_id). | 1–2 days |
| Build FAISS index | Use IndexFlatIP (inner product / cosine) for small scale. For larger: IndexIVFFlat. Save index to disk. | 1 day |
| Implement text_retrieve(question, k=5) | Encodes question, searches FAISS, returns top-k chunks with scores and metadata. | 1 day |
| Test retrieval quality | For 10 questions, manually inspect top-5 retrieved chunks. Confirm relevant passages are retrieved. | 0.5 days |

## 3.3  Retrieval Mode Implementation

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Implement mode T (text-only) | question → text_retrieve(q, k=5) → build_prompt_T(q, chunks) → SLM generate. Return answer string. | 1 day |
| Implement mode T+E | question + hadm_id → text_retrieve + get_patient_snapshot() → build_prompt_TE(q, chunks, snapshot) → SLM generate. | 1 day |
| Implement mode T+E+K | T+E + get_mkg_subgraph(entity_links) → build_prompt_TEK(q, chunks, snapshot, kg_facts) → SLM generate. | 1.5 days |
| Implement prompt templates | Write careful prompt templates for each mode. Include: role instruction, context sections (labeled: [NOTES], [EHR], [KNOWLEDGE]), question, safety instruction ('if insufficient evidence, say so'). | 1 day |
| Measure latency per mode | Time 20 queries per mode. Record mean ± std latency (ms). Record VRAM usage with nvidia-smi at peak. | 0.5 days |
| End-to-end smoke test | Run all 3 modes on 20 sample QA pairs from the router-train set. Inspect outputs. | 1 day |

## 3.4  Phase 3 Deliverables

- QLoRA-tuned Phi-3 Mini (adapter weights saved), with training loss curve

- FAISS index built and saved, covering all note chunks + MKG text descriptions

- All three retrieval modes (T, T+E, T+E+K) implemented and tested

- Prompt templates for each mode (documented in code)

- Latency and VRAM benchmarks per mode (preliminary)

PHASE 4: Adaptive Retrieval Router [Weeks 17–21]

Goal: build and train the router — the central novel contribution. This phase requires careful data management to avoid leakage.

## 4.1  Feature Engineering

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Question type classifier | Train a simple 5-class classifier (diagnosis/test/treatment/explanation/definition) using keyword rules + a small logistic regression on MedQA labels. Output: one-hot or probability vector. | 2 days |
| Keyword features | Binary features: contains_lab_keyword, contains_drug_keyword, contains_diagnosis_keyword. Use a curated keyword list. | 1 day |
| EHR sparsity features | From Phase 1: n_labs, n_diag, d_note, sparsity_bucket (encoded as 0/1/2). Already computed. | 0.5 days |
| KG coverage features | n_mkg_nodes_matched: number of MKG nodes found for this question+patient. n_mkg_edges_retrieved: edges in subgraph. | 0.5 days |
| Retrieval stats features | From text retrieval: max_similarity_score (top-1 chunk score), mean_top5_score, score_entropy across top-5. | 1 day |
| Featurize function | featurize(question, hadm_id) → numpy feature vector of ~15–20 features. Test on 20 examples. | 1 day |

## 4.2  Pseudo-Label Generation (Router Training Set Only)

Run all three retrieval modes on the router-training set (200 questions from router-train patients only). Never touch the held-out eval set here.

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Run T, T+E, T+E+K on router-train set | Generate answers for all 200 questions using each mode. Save answers to JSON. This will take several hours. | 1–2 days |
| Score with automatic metrics | Compute BERTScore F1 for each mode × question. Use a pre-trained BERTScore model (e.g., deberta-large-mnli). | 1 day |
| Score with hallucination heuristics | Apply rule-based hallucination proxy: does the answer contradict any EHR value (labs outside normal range)? Does it recommend a drug listed as contraindicated in the MKG? Label each answer: 0 (clean) / 1 (suspect). | 2 days |
| Compute composite score | score = BERTScore - λ × hallucination_penalty. Try λ = 0.3. Best mode = argmax(score) per question. | 0.5 days |
| Save pseudo-labels | router_train_labels.json: {question_id: {best_mode: 'T+E+K', scores: {...}}}. | 0.5 days |
| Analyze label distribution | Report: how many questions routed to T / T+E / T+E+K. Any class imbalance? If >80% in one class, revisit composite score weighting. | 0.5 days |

⚑ Note: The heuristic hallucination proxy in this phase is just for generating training labels — not the final evaluation. The real hallucination annotation happens in Phase 5.

## 4.3  Router Training

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Train baseline: Random router | Randomly assigns T, T+E, or T+E+K with equal probability. Evaluate on router-val set. This is the lower bound. | 0.5 days |
| Train logistic regression router | sklearn LogisticRegression over feature vectors + pseudo-labels. Tune C on router-val set. | 1 day |
| Train random forest router | sklearn RandomForestClassifier. Tune n_estimators and max_depth on router-val set. | 1 day |
| Train MLP router (optional) | Small 2-layer MLP over features. PyTorch. If RF already performs well, this is optional. | 1.5 days |
| Select best router | Compare all classifiers on router-val set using: routing accuracy, macro F1, and (most importantly) downstream QA quality when router decisions are applied. | 1 day |
| Compute oracle routing (upper bound) | Retrospectively: for each question in router-val set, look up which mode actually performed best. Apply oracle decisions and measure downstream QA quality. This is the ceiling. | 0.5 days |

## 4.4  Router Analysis

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Feature importance analysis | For the selected router, extract feature importances (RF) or coefficients (LR). Which features most predict routing decisions? | 1 day |
| Routing decisions vs sparsity | Pivot table: routing mode assigned vs sparsity bucket. Does the router preferentially use T+E+K for high-sparsity patients? Plot. | 1 day |
| Error analysis | Inspect 20 cases where router chose differently from oracle. What patterns explain the errors? | 1 day |

## 4.5  Phase 4 Deliverables

- Feature engineering code (featurize() function)

- Pseudo-labels for router-train set (saved JSON, documented methodology)

- Trained router (best classifier, with hyperparameter tuning documented)

- Random routing and oracle routing baseline implementations

- Feature importance analysis and routing-vs-sparsity plot

PHASE 5: Hallucination Taxonomy, Annotation & Evaluation [Weeks 22–26]

Goal: build the hallucination evaluation framework — your second major contribution. The held-out eval set is used here for the first time.

## 5.1  Eval Set Answer Generation

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Generate answers for all 4 systems | Run T, T+E, T+E+K, and Router on all 300–500 held-out eval questions. Save all answers. This is the only time you use the eval set. | 1–2 days |
| Generate random routing answers | Apply random router to eval set. Save answers. | 0.5 days |
| Structure output file | eval_outputs.json: per question: {question_id, hadm_id, reference_answer, T_answer, TE_answer, TEK_answer, router_answer, random_answer, sparsity_bucket, question_type} | 0.5 days |

## 5.2  Hallucination Annotation Protocol

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Create annotation guidelines | Write a 2–3 page annotation guide defining each hallucination category with examples. Include decision rules and edge cases. | 2 days |
| Build annotation interface | Simple: a spreadsheet (Google Sheets) with columns for each label, or a Jupyter widget. For each question: show question, EHR snapshot, MKG facts, and the answer to label. | 1 day |
| Annotator 1 labels 300–500 QA pairs | You (Daksh) annotate all pairs: Faithful / Partial / Hallucinated. If hallucinated: EHR-contradicting / KG-contradicting / Unsupported. | 4–6 days |
| Annotator 2 labels same set independently | A second annotator (classmate, colleague, or supervisor) labels the same set without seeing Annotator 1 labels. | 4–6 days (parallel) |
| Compute Cohen's κ | For hallucination detection (binary: hallucinated vs not) and for type classification. Target κ ≥ 0.6. If κ < 0.6, revise guidelines and re-annotate a subset. | 0.5 days |
| Resolve disagreements | Discuss disagreements and reach consensus labels. Document resolution protocol. | 1–2 days |
| Clinical face-validity check | A medically trained reviewer rates 50 randomly selected answers on 3-point scale (Correct / Partial / Incorrect / Unsafe). Record inter-rater agreement. | 1 day (coordinate separately) |

⚑ Note: Start recruiting your second annotator and clinical reviewer early — their availability is a scheduling dependency.

## 5.3  Hallucination Classifier (Optional but Recommended)

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Prepare training data | Use the annotated labels (except held-out test fold). Input: [question + answer + context]. Label: hallucination class. | 1 day |
| Train classifier | Option A: fine-tune a small encoder (e.g., bio_clinicalBERT) for 3-class classification. Option B: use an LLM-based scorer (GPT-3.5 or Claude via API) with a structured prompt. Start with Option B for speed. | 2–3 days |
| Evaluate classifier | 5-fold cross-validation on annotated set. Report F1 per class. | 1 day |
| Use for large-scale analysis | Apply classifier to all eval outputs to get per-mode hallucination rates at scale. | 0.5 days |

## 5.4  Phase 5 Deliverables

- All eval system outputs saved (T, T+E, T+E+K, Router, Random)

- Annotation guidelines document

- Annotated hallucination dataset (300–500 QA pairs with consensus labels)

- Cohen's κ computed and reported

- Clinical face-validity ratings from medically trained reviewer

- Hallucination classifier (optional) with F1 per class

PHASE 6: Experiments, Analysis & Paper Writing [Weeks 27–34]

Goal: compute all results, generate all figures and tables, write the complete paper draft.

## 6.1  Metrics Computation

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Compute BLEU, ROUGE-L, METEOR, BERTScore | For all systems × eval set. Use sacrebleu, rouge-score, nltk.meteor_score, bert_score packages. | 1 day |
| Compute hallucination rates | Per system: overall hallucination rate, EHR-contradicting rate, KG-contradicting rate, unsupported rate. | 0.5 days |
| Compute latency and VRAM | Official benchmark: time 50 eval queries per mode. Record mean ± std. Record peak VRAM via nvidia-smi. | 1 day |
| Compute retrieved token counts | Per mode: average number of tokens in the context window used for generation. | 0.5 days |
| Build main results table | Table: System × Metric (BLEU, ROUGE-L, BERTScore, Hallucination Rate, Latency). Bold the best per column. | 1 day |

## 6.2  Ablation Studies

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Ablation: remove EHR from T+E+K | Run T+K mode (text + KG, no EHR). Measure accuracy + hallucination rate. | 1 day |
| Ablation: remove KG from T+E+K | This is T+E — already computed. No extra work. | 0 days |
| Ablation: remove both | This is T — already computed. No extra work. | 0 days |
| Ablation: router feature groups | Train router with (a) only sparsity features, (b) only question features, (c) all features. Compare val accuracy. | 1 day |
| Ablation: router model type | Compare LR vs RF vs random on val set. Already done in Phase 4 — just compile results. | 0.5 days |

## 6.3  H2 Analysis: KG Benefit vs Sparsity

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Performance vs sparsity bucket | For each system (T, T+E, T+E+K, Router): compute BLEU and hallucination rate separately for low/medium/high sparsity buckets. | 1 day |
| Plot: accuracy vs sparsity | Line chart: x-axis = sparsity bucket, y-axis = BERTScore. One line per system. Expect T+E+K to gain more in high-sparsity. | 0.5 days |
| Plot: hallucination vs sparsity | Same structure: hallucination rate vs sparsity bucket. Expect T to suffer most in high-sparsity. | 0.5 days |
| Plot: router decisions vs sparsity | Bar chart: % of questions routed to each mode (T / T+E / T+E+K), broken down by sparsity bucket. | 0.5 days |
| Answer H2 in text | Write 2–3 sentences answering H2 based on the plots. Does KG help more in high-sparsity? By how much? | 0.5 days |

## 6.4  Paper Writing

| Task | Details / Deliverable | Est. Time |
| --- | --- | --- |
| Write Abstract | 4–6 sentences: problem, method, key result, implication. Write last but plan early. | 1 day |
| Write Introduction | Expand gap analysis memo from Phase 0. Include H1 and H2 explicitly. End with contributions list (numbered). | 2 days |
| Write Related Work | 3 sections: (1) KG-augmented medical RAG (MedRAG, MediGRAF, MedGraphRAG), (2) adaptive/routing RAG (RAGRouter etc.), (3) medical hallucination evaluation. Explicitly state how yours differs. | 2 days |
| Write Methods | Subsections: Lakehouse, MKG Construction, Retrieval Modes, Adaptive Router (feature engineering, training, baselines), Hallucination Taxonomy. | 3 days |
| Write Experimental Setup | Dataset details, data splits, metrics, baselines. Include data split table. | 1 day |
| Write Results | Present main results table, ablation results, H1 answer, H2 analysis. One paragraph per key finding. | 2 days |
| Write Discussion | Interpretation, failure cases (error analysis), clinical implications, limitations. Be candid — reviewers reward honesty. | 1.5 days |
| Write Ethics & Limitations | MIMIC-IV DUA compliance, prototype-only disclaimer, annotation limitations, MKG scope. | 0.5 days |
| Generate all figures | System architecture diagram, sparsity analysis plots, routing decision plots, hallucination breakdown chart. Use matplotlib/seaborn for publication-quality (300 DPI). | 2 days |
| First draft review | Read entire paper. Check: logical flow, claims are backed by tables/figures, contributions list is fully supported by results. | 2 days |
| Supervisor feedback round | Share with Prof. Mushtaq Ahmed. Revise based on feedback. | 1 week |
| Second draft polish | Fix flow, tighten arguments, ensure all citations are correct, check for redundancy. | 2 days |
| Formatting for target venue | Apply CHIL or AMIA LaTeX template. Check page limits (typically 8–10 pages + references). | 1 day |
| Proofread and submit | Final read, spellcheck, figure/table numbering. Submit to arXiv first, then target venue. | 1 day |

## 6.5  Phase 6 Deliverables

- Complete results tables (main + ablations)

- All figures (architecture, sparsity plots, routing plots, hallucination breakdown)

- Complete paper draft in LaTeX (target venue format)

- arXiv preprint submitted

- Code repository cleaned, documented, and made public (where MIMIC licensing allows)

- Annotated evaluation dataset released (hallucination labels, routing decisions)

# Risk Register & Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| MIMIC-IV access delayed > 3 weeks | Medium | Blocks all EHR work | Apply Day 1. Meanwhile, use MIMIC-III demo (100 patients, freely available) to prototype the pipeline. |
| RTX 4050 (6GB) insufficient for Phi-3 Mini | Low–Medium | Blocks fine-tuning | Use 4-bit NF4 + gradient checkpointing. Fallback: Phi-2 (2.7B) or TinyLlama (1.1B). |
| Second annotator unavailable | Medium | Delays Phase 5 by weeks | Recruit annotator by Phase 3. Use GPT-4 as a supplementary annotator with human spot-check. |
| Router class imbalance (all labels same mode) | Medium | Router is trivial; no contribution | Tune composite score λ. Force balanced sampling if needed. Add temperature to mode selection during pseudo-labeling. |
| Cohen's κ < 0.6 after first annotation pass | Medium | Annotation round 2 needed | Budget 1 extra week. Revise guidelines after first 50 items as a calibration round. |
| MKG validation reveals > 30% spurious edges | Low | MKG quality questioned | Use stricter co-occurrence threshold (10% instead of 5%). Focus on ontology-based edges only for core results. |
| Results show router no better than T+E+K | Low–Medium | Weakens main claim | This is still a valid finding — 'always-on KG is sufficient' is publishable. Reframe H1 as empirical study rather than improvement claim. |

# Master Timeline

| Phase | Name | Weeks | Duration | Critical Dependencies | Backup |
| --- | --- | --- | --- | --- | --- |
| 0 | Setup & Literature Review | 1–3 | 2–3 weeks | MIMIC-IV application submitted | MIMIC demo |
| 1 | Lakehouse & EHR Pipeline | 4–7 | 3–4 weeks | MIMIC-IV access approved | — |
| 2 | MKG Construction | 8–11 | 3–4 weeks | Entity linking from MIMIC-IV | Smaller MKG |
| 3 | SLM Fine-tuning & Retrieval | 12–16 | 4–5 weeks | QA datasets ready | Skip fine-tune |
| 4 | Adaptive Retrieval Router | 17–21 | 4–5 weeks | All 3 retrieval modes working | — |
| 5 | Hallucination Annotation | 22–26 | 4–5 weeks | Second annotator recruited | LLM annotator |
| 6 | Experiments & Paper Writing | 27–34 | 5–6 weeks | All results computed | — |
| TOTAL |  | 34 weeks max | ~8 months |  |  |

# Key Quality Gates

Do not proceed to the next phase unless these gates are passed:

| # | After Phase | Gate Criterion |
| --- | --- | --- |
| G0 | Phase 0 → 1 | QLoRA toy fine-tune confirmed working on RTX 4050. MIMIC-IV access applied. |
| G1 | Phase 1 → 2 | get_patient_snapshot() passes 10 manual test cases. Patient ID splits saved and locked. |
| G2 | Phase 2 → 3 | MKG has ≥ 1,000 edges. 50-edge manual validation done with > 80% correctness. |
| G3 | Phase 3 → 4 | All 3 retrieval modes produce coherent answers on 20 test questions. Latency measured. |
| G4 | Phase 4 → 5 | Router outperforms random routing on val set. Routing label distribution is not trivially concentrated (no mode > 75% of labels). |
| G5 | Phase 5 → 6 | Cohen's κ ≥ 0.6. Clinical reviewer has rated 50 answers. All eval outputs generated. |

# Paper Structure (Target: 8 Pages + References)

| Section | Content | Target Length |
| --- | --- | --- |
| Abstract | Problem, approach, key results (H1 answer), implication | ~250 words |
| 1. Introduction | Motivation, gap (no adaptive routing in medical RAG), H1/H2, contributions list | ~1 page |
| 2. Related Work | KG-RAG systems, adaptive RAG, medical hallucination evaluation | ~1 page |
| 3. Methods | Lakehouse, MKG, retrieval modes, router (features + training), hallucination taxonomy | ~2 pages |
| 4. Experimental Setup | MIMIC-IV, splits, baselines, metrics | ~0.5 pages |
| 5. Results | Main table, ablations, H1 answer, H2 sparsity analysis | ~1.5 pages |
| 6. Discussion | Failure cases, clinical implications, when router fails | ~0.5 pages |
| 7. Ethics & Limitations | MIMIC DUA, prototype-only, annotation limitations, MKG scope | ~0.25 pages |
| 8. Conclusion | Summary, answer to H1/H2, future work | ~0.25 pages |
| References | 30–40 citations | ~1 page |

— End of Roadmap —